## Status
DISC DEXPI Continuation Project - Status
Gap Section Label | Task | Additional details | Target Date | Status | %Complete | DONE? | Notes | 26.08.2025 | 08.09.2025 | 15.09.2025 | 22.09.2025 | 29.09.2025 | 06.10.2025 | 13.10.2025 | 20.10.2025 | 27.10.2025 | 03.11.2025
Creation of machine-readable DISC DEXPI Profile | Proposal for a suitable DEXPI extension (Profile RC 1.xml, work in progress) to cover [2] constraints | Label position incl. note Label text Node directions/type/position | 2025-12-19 | In Progess | 90% | 0 | Line styles to be added. | 30% | 30% | 35% | 35% | 40% | 40% | 80% | 85% | 90% | 90%
Creation of machine-readable DISC DEXPI Profile | Extraction of remaining information from the Excel, Drawio, and SVG sources and inclusion in DiscProfile RC 1 |  | 2025-12-19 | In Progess | 97% | 0 | Checking html symbol info, type code enum & node type discussion, finish including description. | 75% | 75% | 80% | 80% | 80% | 90% | 95% | 95% | 95% | 97%
Vessel/Tank Internal Components | Document DEXPI suggestion and present to DEXPI Content Team |  | 2025-09-17 | Complete | 100% | 1 |  | 90% | 90% | 98% | 98% | 100% | 100% | 100% | 100% | 100% | 100%
Vessel/Tank Internal Components | Include updates in DISC DEXPI Requirements document |  | 2025-09-25 | Complete | 100% | 1 | [5 empty] | 10% | 100% | 100% | 100% | 100% | 100%
Vessel/Tank Internal Components | Include updates to DISC DEXPI Profile |  | 2025-10-01 | Complete | 100% | 1 | [5 empty] | 10% | 10% | 20% | 100% | 100% | 100%
Vessel/Tank Internal Components | Include example in Blueprint files |  | 2025-11-01 | In Progess | 20% | 0 | Issue fixed from old versions in-progress | [7 empty] | 10% | 10% | 20%
Annotations | Include example in Blueprint files |  | 2025-09-09 | Complete | 100% | 1 |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Mount Type | Include updates in DISC DEXPI Requirements document | MeasuringSystem only allows 1 MeasuringElement: need a new solution. | 2025-09-17 | Complete | 100% | 1 | Determined that this gap must be solved in a different way. | 60% | 75% | 75% | 85% | 80% | 80% | 100% | 100% | 100% | 100%
Mount Type | Include updates to DISC DEXPI Profile |  | 2025-09-24 | Complete | 100% | 1 | [7 empty] | 100% | 100% | 100% | 100%
Mount Type | Include example in Blueprint files |  | 2025-10-01 | In Progess | 20% | 0 | Issue fixed from old versions in-progress | [5 empty] | 40% | 15% | 15% | 15% | 20%
Duplicate/Incorrect Names | Duplicate/incorrect names Fan/Blower |  | 2025-08-19 | Complete | 100% | 1 | Fixed in DEXPI 2.0 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Duplicate/Incorrect Names | Check and if required raise issue with DEXPI group for UoM usage of bar/bar |  | 2025-09-19 | In Progess | 70% | 0 | Need to add qualifier type to standard ? Discuss with Aibel. | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | 70%
Off-Page Signal management | Discuss and agree on suitable DEXPI model |  | 2025-11-05 | In Progess | 50% | 0 | Available in DEXPI 2.0 xml | 20% | 20% | 20% | 30% | 30% | 30% | 30% | 30% | 50% | 50%
Off-Page Signal management | Document DEXPI suggestion and present to DEXPI Content Team |  | 2025-11-21 | Complete | 100% | 1 | Not needed as can be managed in DEXPI 2.0 | [8 empty] | 100% | 100%
Off-Page Signal management | Include updates in DISC DEXPI Requirements document |  | 2025-11-28 | In Progess | 15% | 0 | [10 empty] | 15%
Off-Page Signal management | Include updates to DISC DEXPI Profile |  | 2025-12-05 | Complete | 100% | 1 | No definition required in profile | [9 empty] | 100%
Off-Page Signal management | Include example in Blueprint files |  | 2025-12-12 | In Progess | 20% | 0 | [10 empty] | 20%
Battery Limits/Tie-ins | Discuss and agree on suitable DEXPI model |  | 2025-09-12 | In Progess | 75% | 0 | Challenge with battery-limits, these are often drafted using vendor limiting 'boxes' connected via nozzles and overlapping signal lines. Suggest to separate out tie-ins from battery-limits. |  |  | 40% | 65% | 75% | 75% | 75% | 75% | 75% | 75%
Battery Limits/Tie-ins | Document DEXPI suggestion and present to DEXPI Content Team |  | 2025-09-19 | In Progess | 20% | 0 |  |  |  | 30% | 30% | 20% | 20% | 20% | 20% | 20% | 20%
Battery Limits/Tie-ins | Include updates in DISC DEXPI Requirements document |  | 2025-10-22 | Not Started |  | 0
Battery Limits/Tie-ins | Include updates to DISC DEXPI Profile |  | 2025-10-29 | Not Started |  | 0
Battery Limits/Tie-ins | Include example in Blueprint files |  | 2025-11-06 | Not Started |  | 0
ProcessSafetyFunction | Document DEXPI suggestion and present to DEXPI Content Team |  | 2025-09-12 | Complete | 100% | 1 | Agreed with Aibel that rules for which sub-type to use will be project specific linked to specific function types. | 70% | 80% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100%
ProcessSafetyFunction | Include updates in DISC DEXPI Requirements document |  | 2025-09-19 | Complete | 100% | 1 | [5 empty] | 60% | 100% | 100% | 100% | 100% | 100%
ProcessSafetyFunction | Include updates to DISC DEXPI Profile |  | 2025-09-22 | Complete | 100% | 1 | [7 empty] | 75% | 100% | 100% | 100%
ProcessSafetyFunction | Include example in Blueprint files |  | 2025-10-29 | Complete | 100% | 1 | [8 empty] | 10% | 10% | 100%
Electrical Line type | Discuss and agree on suitable DEXPI model |  | 2025-09-26 | Complete | 100% | 1 | Not needed .. Use type attribute |  |  | 50% | 80% | 80% | 80% | 80% | 80% | 100% | 100%
Electrical Line type | Document DEXPI suggestion and present to DEXPI Content Team |  | 2025-10-01 | Complete | 100% | 1 | Keep as is with no new sub-types |  |  | 50% | 50% | 50% | 50% | 50% | 50% | 85% | 100%
Electrical Line type | Include updates in DISC DEXPI Requirements document |  | 2025-10-08 | Complete | 100% | 1 | [9 empty] | 15% | 100%
Electrical Line type | Include updates to DISC DEXPI Profile |  | 2025-10-15 | Complete | 100% | 1 | [10 empty] | 100%
Electrical Line type | Include example in Blueprint files |  | 2025-10-22 | Complete | 100% | 1 | [10 empty] | 100%
Motor - Equipment Linking | Include updates in DISC DEXPI Requirements document |  | 2025-09-19 | Complete | 100% | 1 |  | 90% | 90% | 90% | 90% | 90% | 100% | 100% | 100% | 100% | 100%
Motor - Equipment Linking | Include updates to DISC DEXPI Profile |  | 2025-10-08 | Complete | 100% | 1 | [5 empty] | 20% | 20% | 100% | 100% | 100% | 100%
Motor - Equipment Linking | Include example in Blueprint files |  | 2025-10-15 | In Progess | 40% | 0 | [6 empty] | 40% | 40% | 40% | 40% | 40%
Prepare Symbols for Profile | Ensure each symbol is defined in a machine-readable format with correct sizing definitions, connection point definitions. |  | 2025-09-10 | Complete | 100% | 1 | Only those symbols in the correct format will be made available in the profile. Challenge with dash lines/hash Connection points to check and correct. | 85% | 95% | 99% | 99% | 99% | 100% | 100% | 100% | 100% | 100%
Prepare Symbols for Profile | Include updates to DISC DEXPI Profile |  | 2025-09-12 | Complete | 100% | 1 | Automate conversion and add to profile | 80% | 90% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100%
Prepare Symbols for Profile | Label addition to profile | To check Text rotation | 2025-11-12 | In Progess | 95% | 0 | Default L->R for not in-line elements. L->R for in-line or B->T | 20% | 20% | 20% | 20% | 20% | 60% | 95% | 95% | 95% | 95%
Update requirements document | Include DEXPI 2.0 updates |  | 2025-09-12 | Complete | 100% | 1 |  | 60% | 60% | 60% | 60% | 75% | 100% | 100% | 100% | 100% | 100%
DISC collaboration environment | Setup Github environment for storage and collaboration |  | 2025-08-10 | Complete | 100% | 1 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
DISC Workshops and meetings | Plan and schedule workshops& meetings |  | 2025-08-10 | Complete | 100% | 1 |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Blueprint file examples | Convert existing blueprint examples to DEXPI 2.0 |  | 2025-09-12 | In Progess | 99% | 0 |  | 80% | 80% | 95% | 99% | 99% | 99% | 99% | 99% | 99% | 99%
Blueprint file examples | Create blueprint examples for requirements in both serialization formats. |  | 2025-12-19 | Complete | 100% | 1 | [7 empty] | 10% | 10% | 100% | 100%
Verification method | Document verification method. |  | 2025-12-19 | In Progess | 70% | 0 |  | 50% | 50% | 50% | 50% | 50% | 70% | 70% | 70% | 70% | 70%
Symbol definition documentation | Document symbol definition requirements |  | 2025-11-10 | In Progess | 60% | 0 |  | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 60%
LineStyles support in DEXPI | NEW: DEXPI graphical primitives does not support linestyles used in DISC. Add issue to DEXPI content team. |  | 2025-12-19 | Complete | 100% | 1 |  |  |  | 0% | 0% | 0% | 0% | 15% | 70% | 80% | 100%
Complete Workshop 1 | DISC DEXPI workshop at Equinor 2 - days |  | 2025-09-18 | Complete | 100% | 1 |  |  |  |  | 100% | 100% | 100% | 100% | 100% | 100% | 100%